## Sheet1
|  | Expected | [11 empty] | Real
|  | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug
| Workline | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
1. YOLO Model
H | See how to parallelize -> open case | Expected Aug 8 Thu: T &D
H | Check a more powerful one | Expected Aug 8 Thu: T &D
Tunning
M | Calc. as a % the nº of models to train using the random str. | Expected Aug 8 Thu: T &D
L | Understand concept hyper. nº of warm-up epochs
M | Add code total retrain and generalization power | Expected Aug 8 Thu: T &D
H | Dry run | Expected Aug 8 Thu: T &D
| Code union train & val and upload S3 | Expected Aug 8 Thu: T &D
H | Launch the final model | Expected Aug 9 Fri: T &D; Expected Aug 10 Sat: T &D; Expected Aug 11 Sun: T &D; Expected Aug 15 Thu: T &D; Expected Aug 16 Fri: T &D
H | Understand results | Expected Aug 12 Mon: T; Expected Aug 13 Tue: D; Expected Aug 14 Wed: T &D
2. Cost Model
L | tunning | bar: Expected Aug 17 Sat
3. API
H | File claim.py | bar: Expected Aug 9 Fri to Expected Aug 10 Sat
H | Final page.py | bar: Expected Aug 9 Fri to Expected Aug 10 Sat
H | Deployment models | Expected Aug 11 Sun: T &D; Expected Aug 12 Mon: T &D; Expected Aug 13 Tue: T &D
L | Logic for the different scen. | Expected Aug 15 Thu: T; Expected Aug 16 Fri: T; Expected Aug 17 Sat: T &D
4. Documentation
M | Full summary of the YOLO model | bar: Expected Aug 9 Fri to Expected Aug 11 Sun
L | Readme Markdown | bar: Expected Aug 12 Mon to Expected Aug 14 Wed
5. Poster
H | Poster development | bar: Expected Aug 9 Fri to Expected Aug 11 Sun; Expected Aug 14 Wed to Expected Aug 17 Sat
L | Printing
[5 empty] | Work Distribution |  |  |  | Priority
[5 empty] | D | T | T &D |  | H | M | L